## Sheet1
Games Programming Oct 13/14 Feature List
Game Title : Dead Survival
Team Members:
| Count |  | Count
S | 5 | Urgent | 7
M | 14 | High | 10
L | 7 | Medium | 4
XL | 0 | Low | 4 |  |  | # of Tasks for |  |  |  | Items Due Today
N/A | 0 | KIV | 1 | Code | Design | Art | Audio | QA | Research | (9th Jan)
Total | 26 | Total | 26 | 21 | 10 | 13 | 7 | 24 | 21
Feature | Size | Description | Priority | Code | Design | Art | Audio | QA | Research | Deadline | Actioned by
Bullet Appearing at Barrel of Gun | M | Bullet is drawn at the barrel of the gun instead of middle of Player Sprite | Medium | Y | N | N | N | Y | Y | 2013-11-26 | Saklani
Random Spawining of Trees | M | Trees are Randomly Generated Throughout the Map all with Different Sprites | Low | Y | N | Y | N | Y | N | 2013-11-27 | Saklani
Minimap | M | There is a minimap for player to see the surrounding of the safehouse | Low | Y | N | N | N | Y | Y | 2013-11-28 | Saklani
GUI Element Creation | L | Creating GUI Elements for the Game | Urgent | N | Y | Y | N | Y | N | 2013-12-06 | Saklani
Sound Control | M | Controling the Volume of all the sounds in the game | High | Y | N | N | N | Y | Y | 2013-12-06 | Saklani
3 Types of Zombies | M | Have 3 Types of Zombies in the Game | High | Y | N | N | N | Y | N | 2013-12-06 | Saklani
Zombie Path Finding | L | Zombie AI able to navigate through trees | Urgent | Y | N | Y | N | Y | Y | 2013-11-29 | Saklani
Zombie AI Choosing Target for Attack | M | Zombie AI able to Choose to attack building or the player | Urgent | Y | N | N | N | Y | Y | 2013-11-29 | Saklani
Zombie Homing to Player | M | Zombie AI able to follow player | Urgent | Y | N | N | N | Y | Y | 2013-11-29 | Saklani
Zombie Attacking | M | Zombie AI able to attack | Urgent | Y | N | N | N | Y | Y | 2013-11-29 | Saklani
3 Types of Weapons | M | Have 3 Types of Guns in the Game | High | Y | Y | Y | Y | Y | Y | 2013-12-06 | Saklani
Weapon Switching | S | Switch Between Weapons | High | Y | Y | Y | Y | Y | Y | 2013-12-06 | Saklani
Muzzle flash at the tip of barrel of gun when shooting | L | Muzzle flash is to be drawn in all directions the player is facing | KIV | Y | N | N | N | Y | Y | 2013-11-29 | Saklani
Help Screen | M | Instructions Page | Low | Y | Y | Y | Y | Y | Y | 2013-12-06 | Saklani
Building Structures in Game | L | Able to Build Structures in the Game | Medium | Y | Y | Y | Y | Y | Y | 2013-12-06 | Saklani
Pausing of Game | M | Able to Pause Game at choice | Medium | Y | Y | Y | Y | Y | Y | 2013-12-06 | Saklani
Random Spawnining of Supply and Ammo Cache | M | Supply and Ammo Caches Spawn at random at the start of the round | High | Y | N | Y | N | Y | Y | 2013-12-06 | Saklani
Shooting recoil | S | Shooting becomes inaccurate due to recoil | High | Y | Y | Y | N | Y | Y | 2013-11-26 | Saklani
Animation for Button | S | Button have Different Animation when clicked and hovered over | Low | N | Y | Y | Y | Y | Y | 2013-11-29 | Yong Wei
Animation of Player | S | Player animation apears when | Urgent | N | Y | Y | N | Y | Y | 2013-11-26 | Yong Wei
8 Direction Movement | S | Ability to Move in 4 directions | Urgent | Y | N | N | N | Y | Y | 2013-11-26 | Yong Wei
Player Upgrade System | L | Able to Upgrade Player's Stats | High | Y | N | N | N | Y | Y | 2013-12-06 | Yong Wei
LeaderBoard | M | Highscore Page | High | Y | Y | Y | Y | Y | Y | 2013-12-06 | Yong Wei
Loading and Saving Highscore | L | Able to store and retrieve Highscore Data | High | Y | N | N | N | Y | Y | 2013-12-06 | Yong Wei
Main Menu | L | Functional Main Menu for navigation | High | Y | Y | Y | Y | Y | Y | 2013-11-29 | Yong Wei
Audio/Music | M | Sounds/Music for selected actions/events in the game | Medium | Y | N | N | Y | Y | Y | 2013-12-06 | Yong Wei